## Sheet1
Task Name | Duration | Start Date | Finish Date | PIC | Status | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug
Requirement Identification / Scope Clarification | 2 | 2021-02-13 | 2021-02-15 | PM, BA | Complete
Business Case Document (CBA) | 1 | 2021-02-24 | 2021-02-25 | BA | Complete
CBA Approval | 1 | 2021-02-26 | 2021-02-27 | All Related Parties | Not Yet
Market Research | 2 | 2021-02-24 | 2021-02-26 | Product, Marketing | In Progress
Segmentation Product | 2 | 2021-02-22 | 2021-02-24 | Product, Marketing | Complete
Manual Book | 2 | 2021-02-23 | 2021-02-25 | PM, CEO | Complete
Technical Requirement | 0 | 2021-02-21 | 2021-02-21 | BA, SA | Complete
System Design ( Functional Specification Document ) | 8 | 2021-02-22 | 2021-02-24
Entity Relationship Diagram (ERD) | 2 | 2021-02-22 | 2021-02-24 | SA | Complete
Usecase Diagram | 2 | 2021-02-22 | 2021-02-24 | SA | Complete
Activity Diagram | 2 | 2021-02-22 | 2021-02-24 | SA | Complete
Class Diagram | 2 | 2021-02-22 | 2021-02-24 | SA | Complete
System Development | 14 | 2021-02-25 | 2021-03-15
UI/UX Model | 2 | 2021-02-25 | 2021-02-27 | UI/UX Designer | In Progress
Front End Development | 14 | 2021-03-01 | 2021-03-15 | Web Developer | Not Yet
Back End Development | 14 | 2021-03-01 | 2021-03-15 | Mobile Developer | Not Yet | bar: Jul
SIT ( System Integration Testing) | 0 | 2021-03-15 | 2021-03-15
Black Box Testing | 0 | 2021-03-15 | 2021-03-15 | QC, QA, and Developer | Not Yet | bar: Jul
White Box Testing | 0 | 2021-03-15 | 2021-03-15 | QC, QA, and Developer | Not Yet | bar: Jul
UAT ( User Acceptance Testing) | 0 | 2021-03-15 | 2021-03-15
Module 1 | 0 | 2021-03-15 | 2021-03-15 | PM, BA, and User | Not Yet | bar: Jul
Module 2 | 0 | 2021-03-15 | 2021-03-15 | PM, BA, and User | Not Yet | bar: Aug
Module … | 0 | 2021-03-15 | 2021-03-15 | PM, BA, and User | Not Yet | bar: Aug
Deployment System | 1 | 2021-03-16 | 2021-03-17 | PM, BA, and Developer | Not Yet | bar: Aug
Go-live System / Product | 0 | 2021-03-18 | 2021-03-18 | PM, Business user | Not Yet | bar: Aug
Formulas:
Finish Date = WORKDAY([Start Date],[Duration])
Start Date = WORKDAY([Finish Date, row above],1)
Start Date = [Start Date, row below]